## Action Plan & Timeline
[Name of CAD]
Service Lead: [Name]
Operational Support: [Name]
NHS G Public Health Guidance: [Name]
Evaluation Support: [Name]
Action Plan Produced by: [Name]
Date last updated: [Date]
Theme of CAD | [Insert Theme of CAD]
Format of CAD | [Insert Format of CAD] |  |  | Date of CAD: [Insert]
Governance |  |  |  | Planning commenced: [Insert date] |  | [Amend Gantt Chart below to reflect time available]
Actions | Responsibility | Status [RAG] | Last Updated | Update | T - 18W | T - 17W | T - 16W | T - 15W | T - 14W | T - 13W | T - 12W | T - 11W | T - 10W | T - 9W | T - 8W | T - 7W | T - 6W | T - 5W | T - 4W | T - 3W | T - 2W | T - 1W | T - 1D | Day of CAD
Assess Information Governance requirements
Complete Equality Impact Assessment and justify approach
Identify organisational support for event
Identify SLWG to oversee event - ensure this includes all partners (service leads, Trakcare or SIRS teams, outpatient appointment team, third sector organisations, public health for evaluation etc.)
Complete CAD Logic Model and identify resources required for monitoring and evaluation
Create MS Teams channel or folder and ensure all SLWG are included
Identify services included within the event
Shared Learning
Actions | Responsibility | Status [RAG] | Last Updated | Update | T - 18W | T - 17W | T - 16W | T - 15W | T - 14W | T - 13W | T - 12W | T - 11W | T - 10W | T - 9W | T - 8W | T - 7W | T - 6W | T - 5W | T - 4W | T - 3W | T - 2W | T - 1W | T - 1D | Day of CAD
Access CAD Companion on Hi-NET
Consider learning from events outwith Grampian
Funding - Resources & Catering
Actions | Responsibility | Status [RAG] | Last Updated | Update | T - 18W | T - 17W | T - 16W | T - 15W | T - 14W | T - 13W | T - 12W | T - 11W | T - 10W | T - 9W | T - 8W | T - 7W | T - 6W | T - 5W | T - 4W | T - 3W | T - 2W | T - 1W | T - 1D | Day of CAD
Identify resources required for CAD
Identify funding opportunities
Venue for CAD Event
Actions | Responsibility | Status [RAG] | Last Updated | Update | T - 18W | T - 17W | T - 16W | T - 15W | T - 14W | T - 13W | T - 12W | T - 11W | T - 10W | T - 9W | T - 8W | T - 7W | T - 6W | T - 5W | T - 4W | T - 3W | T - 2W | T - 1W | T - 1D | Day of CAD
Identify venue
Agree date and time
Create floor plan of venue
Identify equipment and furniture required
Arrange onsite visit before pre-run
Organise pre-run at venue before event
Create wayfinding signs
Organise catering (coffee, tea, cups etc.)
The Big Conversation
Actions | Responsibility | Status [RAG] | Last Updated | Update | T - 18W | T - 17W | T - 16W | T - 15W | T - 14W | T - 13W | T - 12W | T - 11W | T - 10W | T - 9W | T - 8W | T - 7W | T - 6W | T - 5W | T - 4W | T - 3W | T - 2W | T - 1W | T - 1D | Day of CAD
Agree format of Big Conversation
Agree venue(s)
Agree target groups
Agree date(s) for engagement
identify questions to guide Big Conversation
Create poster
Create MS Form/QR Code for booking
Identify circulation list
Create MS Form/QR Code for feedback
Hold the Big Conversation
Collate responses
Service User Reference Group
Actions | Responsibility | Status [RAG] | Last Updated | Update | T - 18W | T - 17W | T - 16W | T - 15W | T - 14W | T - 13W | T - 12W | T - 11W | T - 10W | T - 9W | T - 8W | T - 7W | T - 6W | T - 5W | T - 4W | T - 3W | T - 2W | T - 1W | T - 1D | Day of CAD
E-mail people who attended the Big Conversation & invite them to attend Service User Reference Group.
Send all communications & draft documents to SURG for comments throughout process.
Invite group to any pre-runs to check implications for layout.
Arrange post-event feedback session & agree next steps
Create MS Form for post-event feedback
Volunteers/Facilitators
Actions | Responsibility | Status [RAG] | Last Updated | Update | T - 18W | T - 17W | T - 16W | T - 15W | T - 14W | T - 13W | T - 12W | T - 11W | T - 10W | T - 9W | T - 8W | T - 7W | T - 6W | T - 5W | T - 4W | T - 3W | T - 2W | T - 1W | T - 1D | Day of CAD
Identify sources of volunteers/facilitators for the event (NHSG service staff, venue staff etc.)
Approach identified sources for volunteers/facilitators
Produce briefing sheet for volunteers - "What to expect on the day" and role requirements, suggested lines etc.
Send volunteers briefing sheet and invite them to pre-run
Patient Population/Letters & Appointments
Actions | Responsibility | Status [RAG] | Last Updated | Update | T - 18W | T - 17W | T - 16W | T - 15W | T - 14W | T - 13W | T - 12W | T - 11W | T - 10W | T - 9W | T - 8W | T - 7W | T - 6W | T - 5W | T - 4W | T - 3W | T - 2W | T - 1W | T - 1D | Day of CAD
Identify patient cohort
(If required) Liaise between service and Trakcare team regarding quick clinic, outcomes and coding for administration & evaluation
Agree whether open event, invitation only or hybrid
Agree number of slots available
Agree booking form
Agree how appointment details will be sent out
Create informational leaflet, using community engagement feedback, to go with opt-in letter
Send informational leaflets/opt-in letter
Draft appointment letter
Send out appointment letter to patients that have opted-in (ensure letter includes option to opt-out).
Review uptake of appointments weekly - phone calls to initial invitees, widening invitation list etc. can help maximise appointment uptake
Communication Plan/Promotion
Actions | Responsibility | Status [RAG] | Last Updated | Update | T - 18W | T - 17W | T - 16W | T - 15W | T - 14W | T - 13W | T - 12W | T - 11W | T - 10W | T - 9W | T - 8W | T - 7W | T - 6W | T - 5W | T - 4W | T - 3W | T - 2W | T - 1W | T - 1D | Day of CAD
Communicate with GPs
Social media posts to advertise event (NHS Grampian/Health & Social Care Partnership/Local Authority etc.)
Share with local third sector organisations to promote
Patient Passports & What Matters to You? Conversations
Actions | Responsibility | Status [RAG] | Last Updated | Update | T - 18W | T - 17W | T - 16W | T - 15W | T - 14W | T - 13W | T - 12W | T - 11W | T - 10W | T - 9W | T - 8W | T - 7W | T - 6W | T - 5W | T - 4W | T - 3W | T - 2W | T - 1W | T - 1D | Day of CAD
Create Patient Passport and template for WMTY conversations - develop following completion of logic model/evaluation framework
Create MS Form for Patient Passport (only to be used by admin for transcribing data)
Recruit Community Connectors (engagement teams, wellbeing teams, adjacent services etc.)
Create briefing sheet with prompts for discussion for WMTY conversation
Email stall holders asking for any text, video or visual material they wish displayed
Create map and info sheet of stall holders for attendees and WMTY conversations
Create name cards & table numbers for Community Connectors
Community Partners
Actions | Responsibility | Status [RAG] | Last Updated | Update | T - 18W | T - 17W | T - 16W | T - 15W | T - 14W | T - 13W | T - 12W | T - 11W | T - 10W | T - 9W | T - 8W | T - 7W | T - 6W | T - 5W | T - 4W | T - 3W | T - 2W | T - 1W | T - 1D | Day of CAD
Identify community partners for event
Write to community partners to ask if they are able to attend event
Create community partner briefing sheet
Produce final list of community partners
Arrange for delivery of leaflets for each stall
Patient Check-In and Check-Out
Actions | Responsibility | Status [RAG] | Last Updated | Update | T - 18W | T - 17W | T - 16W | T - 15W | T - 14W | T - 13W | T - 12W | T - 11W | T - 10W | T - 9W | T - 8W | T - 7W | T - 6W | T - 5W | T - 4W | T - 3W | T - 2W | T - 1W | T - 1D | Day of CAD
Create list of final attenders and appointment times
Identify admin staff to support patient check-in and check-out
Generate CAD numbers for attendees
Photocopy personal passport on leaving to allow transcription to MS Form
Feedback Sessions
Actions | Responsibility | Status [RAG] | Last Updated | Update | T - 18W | T - 17W | T - 16W | T - 15W | T - 14W | T - 13W | T - 12W | T - 11W | T - 10W | T - 9W | T - 8W | T - 7W | T - 6W | T - 5W | T - 4W | T - 3W | T - 2W | T - 1W | T - 1D | Day of CAD
Identify staff to help attendees complete feedback
Identify space at venue for attendees to complete feedback
Contact corporate communications to take media of event
Evaluation
Actions | Responsibility | Status [RAG] | Last Updated | Update | T - 18W | T - 17W | T - 16W | T - 15W | T - 14W | T - 13W | T - 12W | T - 11W | T - 10W | T - 9W | T - 8W | T - 7W | T - 6W | T - 5W | T - 4W | T - 3W | T - 2W | T - 1W | T - 1D | Day of CAD
Complete CAD Evaluation Framework and ensure appropriate questions for capturing data are included in feedback section of Patient Passport
Create feedback form for staff, services and community partners
Complete interval follow-up per CAD Evaluation Framework

## SLWG
Name | Title | Organisation | Email Address | Tel Contact

## Stallholders
Table | Organisation | Contact Name | Contact E-mail | Contact Number | Can attend event? | Table Number | Notes

## Funding
Costings for Community Appointment Day
Costs £
Promotion & Advertising | 1 Event | 2 Events (Test of Change)
Total | 0 | 0
Catering
Tea Bags
Coffee Sachets
Sugar Sachets/Sweeteners
Milk
Coffee Cups
Stirrers
Water Flasks
Fruit
Total | 0 | 0
Travel & Volunteer Expenses
Travel expenses for people with Lived Experience/ Volunteers & Charities coming from further afield - the Big Conversation / CAD | 0 | 0
Volunteer Fleeces (12)
Total | 0 | 0
Venue Hire
Room Hire (Note ACVC free of charge) Other locations will be chargable | 0 | 0
Transprot (For external locations)
| 0 | 0
| 0 | 0
Total | 0 | 0
Stationary for Events
Total | 0 | 0
Total Costs | 0 | 0

## Resources
Resources (Template)
The Big Conversation | Number Needed | Number Obtained | Status [RAG]
Laptop for presentations
Copy of presentations downloaded
Programme
Conversation questions (one set for each table)
Copies of opt-in letter
Copies of pre-information sheets
Copy of Patient Passport
Facilitators Briefing Sheet
Pens
Sheets of paper
Tables
Chairs
Projector
Community Appointment Day
Check in Area | Number Needed | Number Obtained | Status [RAG]
Laptops
Paper copies of appointment times
List of CAD numbers
What matters to you Conversation Area | Number Needed | Number Obtained | Status [RAG]
Paper copies of questionnaire
Clipboards & pens
List of organisations attending and what support they provide.
Table numbers
Name of individual facilitating the conversation on a stand
WMTY conversation packs
Copies of floor plan/stallholder map
Volunteers/Facilitators | Number Needed | Number Obtained | Status [RAG]
Meet and Greeters
Wayfinders
Community Connectors
Catering volunteers
Volunteer lanyards
Volunteers briefing sheets
Volunteer expenses
Signage | Number Needed | Number Obtained | Status [RAG]
Direction of flow signs
CAD banners
Check Out Area | Number Needed | Number Obtained | Status [RAG]
Laptops for transcription
Admin staff for data entry
Admin staff for scanning
Benchmarker
Clinical | Number Needed | Number Obtained | Status [RAG]
Screens
Chairs
Couches
Boxes of gloves
Wi-Fi | Number Needed | Number Obtained | Status [RAG]
Wi-fi password for staff and volunteers on briefing sheet
Community Partners | Number Needed | Number Obtained | Status [RAG]
Tables
Chairs
Floor Plan
Catering | Number Needed | Number Obtained | Status [RAG]
Tea Bags
Coffee Sachets
Sugar sachets/sweeteners
Milk
Coffee Cups
Stirrers
Water Flasks

## BC Survey List
Organisation or Individual | Contact Name | Contact E-mail | Contact Number

## Service User Group
Contact Name | Contact E-mail | Contact Number | Can attend pre-run | Can attend CAD

## Floor Plan
[Insert Floor Plan Once Known]

## Appointments
Time | Action | Capacity | Number currently booked | Time | Action | Time | Action | Time | Action | Time | Action
Example:12:30 | Arrival and check-in | 15 | 12 | 12:45 | WMTY conversations | 13:15 | Talks | 13:40 | Stalls | 14:30 | Check-out